## Sheet1
Change Request Form
S. No. | Date | Main Menu / Sub Menu | Change / Correction Details | CR / Issue | Dev Status | Dev By | Verified Status | Remarks
1 | 2020-06-08 | Sampling & Dev - Analyze Mat List | Material Name, Description and Finish should come from Material Master as one entry | CR | Pending / Done | Rohit / Satendra | Ok / Not Ok
2 | 2020-06-05 | Samplin & Dev - Sampling Material Requisition | The style number gets removed in case we go and edit the already created record | Issue | Done | Rohit / Satendra
3 | 2020-06-05 | Samplin & Dev - Sampling Material Requisition | There is no check between the requested date and the expected date. The expected date and receive date should never be before the request date. | CR | Done | Rohit / Satendra
4 | 2020-06-05 | Samplin & Dev - Sampling Material Requisition | Record should not be saved if user has not entered the requirement details | Issue | Done | Rohit / Satendra
5 | 2020-06-05 | Samplin & Dev - Sampling Material Requisition | Print formats to be made for the requestion request | CR |  | Rohit / Satendra
6 | 2020-06-05 | Samplin & Dev - Sampling Material Requisition | Material/Item Name is not there on the screen | Issue |  | Rohit / Satendra
7 | 2020-06-05 | Samplin & Dev - Sample Requisition | If any material requistion is made, the record is automatically reflected on the Sample Requistion Screen, which should not be there | CR | Done | Rohit / Satendra
8 | 2020-06-05 | Samplin & Dev - Sample Requisition | Expected date is not getting saved on the screen | Issue | Done | Rohit / Satendra
9 | 2020-06-05 | Samplin & Dev - Sample Requisition | Provision to check the sample status (Done or Pending) | CR |  | Rohit / Satendra
10 | 2020-06-08 | Style Creation | OCD on Style Creation Screen, Date filter needs to be checked | Issue | Done
11 | 2020-06-09 | Pre Order Cost - Excel Sheet | Wrong style number in one column. | Issue | Done
12 | 2020-06-09 | Pre Order Cost - Excel Sheet | Image issue | Issue
13 | 2020-06-09 | Pre Order Cost- Excel Sheet | Values of Production Cost (CM,Printing, Embroidery, Washing, Testing): No link between the values put through screen directly and the values in sheet. | Issue
14 | 2020-06-09 | Pre Order Cost- Excel Sheet | Discount % field is not in excel | Issue
15 | 2020-06-09 | Pre Order Cost | The values on the screen are getting added on the main product cost even if the option to not add them into final cost is selected. | Issue
17 | 2020-06-09 | Style Creation | Style name doesn't change on the main screen if any rectification is done | Issue
18 | 2020-06-09 | Buyer Master | Unable to edit CPM | Issue
20 | 2020-06-09 | TNA Stage Master | Clone option needed, to edit the already created Template | CR | Done
21 | 2020-06-11 | Cost Sheet to Buyer | Production Cost not coming on the "Cost sheet to buyer screen" | Issue | Done
22 | 2020-06-12 | Pre Order Cost | The the value should be changed to 4 places of decimal | Issue | Done
23 | 2020-06-13 | TNA Stage Master | Seperate Activity Master, to edit already created TNA
24 | 2020-06-13 | Buyer Master | All styles are visible on the style information in the Buyer master irrespective of their brand/buyer | Issue | Done
25 | 2020-06-15 | Fields required in Buyer Master | Buyer/ Brand Logo, Commission percentage, Invoice Type, PAN No, Credit Period, Insurance Status, Delivery Terms, Payment Terms | CR
26 | 2020-06-15 | Pre Order Cost | Back Button on Pre-Order Cost and Cost sheet to buyer | Issue
27 | 2020-06-15 | Buyer Master - Company Information | Business segment and Product category dropdown on Buyer Master are not working. | Issue | Done
28 | 2020-06-16 | Buyer Master - | Unable to attach document in the document management field |  | Done
29 | 2020-06-16 | Merchandising - BOM | TTL Order Lead Time -( Ex-Factory end date - OCD), TTL Fabric Lead Time - (Fabric Inhouse Start Date-OCD), TTL Merchandising Lead Time -(File Handover Date - OCD), Production Lead Time - (Ex-factory Start Date- Cutting Start Date)
30 | 2020-06-22 | Dashoard Changes | Change the headers of the existing dashboard and add new ones | CR | WIP
Supply Chain Coverage chart is pending
31 | 2020-06-24 | Style | Ex-factory on the style screen should be the first ex-factory (linked to the TNA ex-factory start activity) | CR
32 | 2020-06-24 | BOM | Incorrect dates on the BOM Screen (Actual inhouse date, in house date...)
33 | 2020-06-24 | BOM | Can we freeze the one column on BOM screen like Material Name, so that it helps to fill information
34 | 2020-06-24 | Supplier Master | In trims section only supplier marked as trim should be visible (may or may not be iscussion to be required)
35 | 2020-06-24 | Buyer Confirmation/PO | Unable to edit placement quantity in Buyer PO
36 | 2020-06-24 | Edit Style Detail | Quantity by color should not be greater than placement quantity
37 | 2020-06-24 | Indent | Incorrect calculation on order quantity ,total allowance percentage on the indent screen
38 | 2020-06-24 | Indent | If any item is marked to be segregated size wise, than the color column shows "undefined"
39 | 2020-06-24 | Indent | order quantity should not be higher than the required quantity, insome exceptional cases only admin should have the right to change the allowance percentage if extra quantity needs to be ordered.
40 | 2020-06-24 | Pending PO | Option to check/view & change the PO before releasing it.
41 | 2020-06-24 | Pending PO/Released PO | Buyer Name should be added on both screen
42 | 2020-06-24 | Pending PO | Save and Back button on relesed PO
43 | 2020-06-24 | Released PO | After PO is released if the PO has been mailed/ sent to supplier it can be shown in status